## Sheet1
Time Estimate for Project Name
SL No | Project | Phase | Project Module | Project Sub Module | Progress | Hours Total 50 | Start Date | End Date | Proposed End Date | Status
1 | Stadium Ticket Booking | Design Phase | User | Login | Login Page contains username and password with a login button that helps to log into the application on the user side | 2 | 2022-07-25 | 2022-07-25 |  | Completed
2 | Stadium Ticket Booking | Design Phase | User | Registration | registration form conatin usename email password and retype password also login with google is also provided | 3 | 2022-07-25 | 2022-07-25 | 2022-07-26 | Completed
3 | Stadium Ticket Booking | Design Phase | User,Admin | payment page and home page | payment page, which pay using card. | 3 | 2022-07-27 |  | 2022-07-28 | completed
4 | Stadium Ticket Booking | Design Phase | User,Admin | about,feedback |  | 2.5 | 2022-07-28 |  | 2022-07-29 | pending
5 | Stadium Ticket Booking | Design Phase |  |  |  | 1 | 2022-07-28 | 2022-07-28
6 | Stadium Ticket Booking | Design Phase |  |  |  | 1 | 2022-07-29 | 2022-07-29
7 | Stadium Ticket Booking | Design Phase |  |  |  | 1 | 2022-07-30 | 2022-07-30
8 | Stadium Ticket Booking | Design Phase |  |  |  | 1 | 2022-07-31 | 2022-07-31
9 | Stadium Ticket Booking | Design Phase |  |  |  | 1 | 2022-08-01 | 2022-08-01
10 | Stadium Ticket Booking | Design Phase |  |  |  | 1 | 2022-08-02 | 2022-08-02
11 | Stadium Ticket Booking | Design Phase |  |  |  | 1 | 2022-08-03 | 2022-08-03
12 | Stadium Ticket Booking | Design Phase |  |  |  | 1 | 2022-08-04 | 2022-08-04
13 | Stadium Ticket Booking | Design Phase |  |  |  | 1 | 2022-08-05 | 2022-08-05
1 | Stadium Ticket Booking | Development Phase |  |  |  | 2 | 2022-08-06 | 2022-08-06
2 | Stadium Ticket Booking | Development Phase |  |  |  | 2 | 2022-08-07 | 2022-08-07
3 | Stadium Ticket Booking | Development Phase |  |  |  | 2 | 2022-08-08 | 2022-08-08
4 | Stadium Ticket Booking | Development Phase |  |  |  | 2 | 2022-08-09 | 2022-08-09
5 | Stadium Ticket Booking | Development Phase |  |  |  | 2 | 2022-08-10 | 2022-08-10
6 | Stadium Ticket Booking | Development Phase |  |  |  | 2 | 2022-08-11 | 2022-08-11
7 | Stadium Ticket Booking | Development Phase |  |  |  | 1 | 2022-08-12 | 2022-08-12
8 | Stadium Ticket Booking | Development Phase |  |  |  | 2 | 2022-08-13 | 2022-08-13
9 | Stadium Ticket Booking | Development Phase |  |  |  | 2 | 2022-08-14 | 2022-08-14
10 | Stadium Ticket Booking | Development Phase |  |  |  | 2 | 2022-08-15 | 2022-08-15
11 | Stadium Ticket Booking | Development Phase |  |  |  | 2 | 2022-08-16 | 2022-08-16
12 | Stadium Ticket Booking | Development Phase |  |  |  | 2 | 2022-08-17 | 2022-08-17
13 | Stadium Ticket Booking | Development Phase |  |  |  | 1 | 2022-08-18 | 2022-08-18
1 | Stadium Ticket Booking | Testing Phase |  |  |  | 1 | 2022-08-19 | 2022-08-19
2 | Stadium Ticket Booking | Testing Phase |  |  |  | 1 | 2022-08-20 | 2022-08-20
3 | Stadium Ticket Booking | Testing Phase |  |  |  | 1 | 2022-08-21 | 2022-08-21
4 | Stadium Ticket Booking | Testing Phase |  |  |  | 1 | 2022-08-22 | 2022-08-22
5 | Stadium Ticket Booking | Testing Phase |  |  |  | 1 | 2022-08-23 | 2022-08-23
6 | Stadium Ticket Booking | Testing Phase |  |  |  | 1 | 2022-08-24 | 2022-08-24
7 | Stadium Ticket Booking | Testing Phase |  |  |  | 1 | 2022-08-25 | 2022-08-25
8 | Stadium Ticket Booking | Testing Phase |  |  |  | 1 | 2022-08-26 | 2022-08-26
9 | Stadium Ticket Booking | Testing Phase |  |  |  | 1 | 2022-08-27 | 2022-08-27
10 | Stadium Ticket Booking | Testing Phase |  |  |  | 1 | 2022-08-28 | 2022-08-28
11 | Stadium Ticket Booking | Testing Phase |  |  |  | 1 | 2022-08-29 | 2022-08-29
12 | Stadium Ticket Booking | Testing Phase |  |  |  | 1 | 2022-08-30 | 2022-08-30
13 | Stadium Ticket Booking | Testing Phase |  |  |  | 1 | 2022-08-31 | 2022-08-31